## Slide 1: FY 23-24 Budget Committee
Planning Meeting
January 26, 2023
.

## Slide 2: Welcome, Budget Committee Members
Returning Members
Jill Vales, Chair (7-311)
Howie Allen (14-305)
Bob Knowles (3-211)
New Members
Frank Pedro (8-309)
Kimberly Cobaugh (2-311)
Brian Forsythe (26-310)
Self-Introductions

## Slide 3: Budget Major Milestones
Budget Committee:
  Individual Assignments
  Small Group Working Sessions
  Budget Committee Open Meetings
Insurance Premiums Estimates Received
Budget Workshop with Full Board
Board Votes on Operating Budget and Minimum Reserve Funding %
Owner’s Votes on Reserve Funding
  Mailing to Owners
  Owners’ Vote on Overriding 100% Reserve Funding

## Slide 4: Budget Committee Responsibilities
Preliminary Major Assumptions for Operating Budget
Detailed Calculations and Budget Templates Completion
Review Insurance Premiums and Contracted Expenses Estimates
Review Proposed Personnel Expenses Line Items
Calculate Allocations of Common Expenses to Buildings
Reserves Calculations & Proposed Minimum Assessment %s
Budget Workshop for Board of Directors (Open)
Review Assessment Calculations by Unit
Note. CRI’s contract does not include Budget preparation assistance;
assistance available for an additional fee.

## Slide 5: CRI & LCG Staff Responsibilities
CRI to Record all 6-30-2022 Audit Adjustments, by Building January
LCG PM and Office Staff:
  Analytical Review/Adjustment of 12-31-2022 Amounts (with Howie & Jill - January)
  Prepare Budget Templates including 12-31-2022 6-Month Actuals (Feb.)
  Calculate Proposed Personnel Expenses (Feb.)
  Provide Estimated Costs for all Contracted Expenses (Feb.)
  Obtain Insurance Premiums Estimates (March or April)
  Other: (April and/or May 2023)
    Calculations of Assessments by Unit
    Notices and Mailing
    Unit Owner Voting
  Enter New Assessments into Topps (June)

## Slide 6: Budget Excel Templates
LCG Office Staff:
  FYE 2022 Actual/Audited Amounts
  FY 2023 Budget Amounts
  FYTD 12-31-2022 Actual Amounts
    After any Corrections/Adjustments
Budget Committee:
  FYE 2023 Projected Operating Amounts
    Considering the Actual Timing of Expenses that are Not the Same Monthly
  FYE 2024 Budgeted Operating Amounts
    Based on Major Assumptions
    Based on Estimated Insurance and Contract Expenses Amounts
  FYE 2024 Budgeted Reserve Assessments

## Slide 7: Teamwork, Quality Control & Succession Planning

## Slide 8: Committee Assignments: 4 Small Groups
Committee Chair - Jill
  Schedule Committee Meetings
  Develop PowerPoint Presentations
  Facilitate Committee Meetings and Budget Workshop
Common Operating Budget: Jill & Kim*
  Including Allocation of Common Expenses to Buildings
Buildings Operating Budgets: Howie, Bob & Brian*
  Update Historical Water Analysis
  Elevator Door Monitor – New Revenue and Expense Line Items
  Washers and Dryers Replacements?
Reserves Calculations and Assessments: Frank & Brian*
  Update Remaining Useful Lives
  Update Reserve Balances Projected for 6-30-2023
  Analyze Potential Future Impacts re Roofs and Structural Elements
  Calculate 100% Funding Amounts and Assessments
  Calculate Lesser % Funding Amounts and Assessments
  * Added at Meeting
4. Review Property Manager’s Schedules and Calculations of Assessments by Unit
– All*

## Slide 9: Major Assumptions TBD
Numbers of Units to be Sold (Impacts Other Income)
Staff Positions
Pay Increase Percentages
Insurance Premiums Increase Percentage
Elevator Door Monitors: Special Assessment?
General Inflation for Expenses
Governing Documents Project?
Special Projects?
Special Requests?
Contingency
Reserve Funding Percentages
Bus Driver?*
Rent on Unit 20B-106*
Activities* *Added at Meeting

## Slide 10: Proposed Work Schedule
Committee Meetings
Regular Open Committee Meetings
  Establish Schedule ASAP
    Date and Time – 2/15/2023 at 10:00 am*
    Location – Auditorium*
  Review Progress on Assignments
  Share Draft Completed Templates
  Ask Questions
  Discuss Assumptions
  Make Recommendations
Other Meetings and Activities
Small Group Working Sessions
  As Needed
  Closed
Committee Work Substantially Finished
  Late March
Budget Workshop for Board Members
  Open
  Late March or April
    Depending on Timing of Insurance Premiums Estimates
Other: Late April
  Board Votes
  Assessment Calculations by Unit
  Mailings to Owners
  Owner Votes on Reserves: April or May
    Recommend Electronic Voting be Allowed
This Photo by Unknown Author is licensed under CC BY
Easter is April 9
*Added at Meeting

## Slide 11: Discussion and Ongoing Communications
Comments
Suggestions
Requests
Confidentiality*
Shared Documents – Dropbox – Yes*
Committee Email? – No*
Next Committee Meeting Date – 2/15/2023*
Sign-in Sheet with Contact Info.
* Added at Meeting